## Product Backlog
AAC System - Product Backlog
Project: AI-Powered AAC System for Children with ASD (Sinhala/Tamil/English)
# | Backlog Item | Priority | Target Sprint
1 | Literature review and requirements analysis | High | Sprint 1
2 | System architecture and technology selection | High | Sprint 1
3 | Flutter project setup (Android and iOS targets) | High | Sprint 1
4 | Symbol grid, navigation, and basic AAC flow | High | Sprint 2
5 | Trilingual UI framework (Sinhala, Tamil, English) | High | Sprint 2
6 | Basic TTS integration | Medium | Sprint 2
7 | Firebase project setup (exploratory) | Medium | Sprint 2
8 | AI model pipeline setup and initial training | High | Sprint 2-3
9 | Full model training and TFLite export | High | Sprint 3
10 | Platform B FER integration | High | Sprint 3
11 | Emotion-adaptive vocabulary logic | Medium | Sprint 3
12 | Dashboard completion | Medium | Sprint 4
13 | Ethics application and approval | High | Sprint 4
14 | Pilot protocol and participant recruitment | Medium | Sprint 4
15 | Pilot execution and data collection | High | Sprint 5
16 | Final report and deliverables | High | Sprint 5

## Sprint Backlogs
AAC System - Sprint Backlogs
Sprint 1 (Nov - Dec 2025) - Completed
# | Task | Status
1 | Complete literature review (ASD, AAC, FER, Sri Lankan context) | Done
2 | Gather requirements from literature and informal stakeholder discussions | Done
3 | Design system architecture (dual-platform, offline-first) | Done
4 | Select technology stack (Flutter, TensorFlow, Firebase) | Done
5 | Initialise Flutter project with Android and iOS build targets | Done
6 | Produce design artefacts (architecture, ER, use case, class diagrams) | Done
Sprint 2 (Jan - Feb 2026) - Completed
# | Task | Status
1 | Implement symbol grid interface with category navigation | Done
2 | Implement trilingual switching framework (English complete, Sinhala/Tamil partial) | In Progress
3 | Integrate basic text-to-speech (English functional, Sinhala/Tamil under evaluation) | In Progress
4 | Set up local data layer (SQLite, JSON vocabulary files) | Done
5 | Create Firebase project and explore configuration | Done
6 | Begin AI model pipeline setup (ahead of schedule from Sprint 3) | Done
7 | Run preliminary training experiments on public datasets | Done
8 | Conduct initial field exposure at Karapitiya Teaching Hospital | Done
9 | Implement basic unit and widget tests | Done
10 | Upload APK to Google Play Console for internal testing | Done
Sprint 3 (Mar 2026) - Current
# | Task | Status
1 | Finalise symbol set and resolve licensing | In Progress
2 | Complete Sinhala and Tamil vocabulary | Pending
3 | Evaluate alternative TTS engines for Sinhala/Tamil | Pending
4 | Complete curated dataset (2,000-5,000 images) | Pending
5 | Full model training with hyperparameter tuning | Pending
6 | TFLite export and on-device benchmarking | Pending
7 | Submit ethics application | In Preparation
Sprint 4 (Apr 2026) - Planned
# | Task | Status
1 | Integrate FER pipeline into Flutter application | Pending
2 | Implement emotion-adaptive logic and caregiver override | Pending
3 | Complete therapist-parent dashboard | Pending
4 | Follow up on ethics approval | Pending
5 | Design pilot protocol and recruit participants | Pending
Sprint 5 (May 2026) - Planned
# | Task | Status
1 | Conduct supervised pilot at Karapitiya Teaching Hospital | Pending
2 | Collect quantitative and qualitative data | Pending
3 | Analyse pilot findings | Pending
4 | Write final report and compile deliverables | Pending
5 | Prepare and deliver final presentation | Pending

## Sprint Tracker
AAC System - Sprint Progress Tracker
Current Sprint: Sprint 3 (Mar - Apr 2026) ¦ Last updated: 25 March 2026
Sprint | Backlog | To Do | In Progress | Review | Done
Sprint 1 Nov-Dec 25 |  |  |  |  | Literature review Requirements analysis System architecture Tech stack selection Flutter project setup Design artefacts
Sprint 2 Jan-Feb 26 |  |  | Trilingual switching Sinhala/Tamil TTS |  | Symbol grid UI Local data layer Firebase setup AI pipeline setup Preliminary training Karapitiya visit Unit tests Play Console upload
Sprint 3 Mar 26 | Sinhala/Tamil vocab TTS evaluation Dataset curation Model training TFLite export | Ethics application | Symbol set licensing
Sprint 4 Apr 26 | FER integration Emotion-adaptive logic Dashboard Ethics follow-up Pilot protocol
Sprint 5 May 26 | Pilot execution Data collection Analysis Final report Presentation
Legend:
Completed
In Progress
Pending / Backlog

## Sprint Summary
AAC System - Sprint Progress Summary
Sprint | Period | Total Tasks | Done | In Progress | Pending | Completion %
Sprint 1 | Nov - Dec 2025 | 6 | 6 | 0 | 0 | 100%
Sprint 2 | Jan - Feb 2026 | 10 | 8 | 2 | 0 | 80%
Sprint 3 | Mar 2026 | 7 | 0 | 1 | 6 | In Progress
Sprint 4 | Apr 2026 | 5 | 0 | 0 | 5 | 0%
Sprint 5 | May 2026 | 5 | 0 | 0 | 5 | 0%
Overall Progress: 14 of 33 tasks completed (42%). Sprint 3 in progress (as of 25 March 2026). Project deadline: May 2026.

## Milestones
AAC System - Milestone Tracker
# | Milestone | Planned Date | Actual Date | Status | Notes
1 | Project proposal approved | Nov 2025 | Nov 2025 | Done | Approved by supervisor
2 | Literature review completed | Dec 2025 | Dec 2025 | Done
3 | System architecture finalised | Dec 2025 | Dec 2025 | Done | Dual-platform, offline-first
4 | Flutter project initialised | Dec 2025 | Dec 2025 | Done | Android + iOS targets
5 | Core AAC interface functional | Feb 2026 | Jan 2026 | Done | Completed ahead of schedule
6 | AI pipeline setup | Feb 2026 | Jan 2026 | Done | Moved ahead from Sprint 3
7 | Karapitiya field exposure | Feb 2026 | Feb 2026 | Done | Exploratory visit, no data collected
8 | Play Console internal testing | Feb 2026 | Feb 2026 | Done | APK uploaded, internal track
9 | Interim report submission | Feb 2026 | Mar 2026 | Done | Current submission
10 | Symbol set finalised | Mar 2026 | - | In Progress | Licensing under discussion
11 | Ethics application submitted | Mar 2026 | - | In Preparation | Forms prepared, awaiting submission
12 | Full model training completed | Mar 2026 | - | Pending | Dependent on curated dataset
13 | Platform B FER integration | Apr 2026 | - | Pending | After model training
14 | Ethics approval received | Apr 2026 | - | Pending | External dependency
15 | Pilot study conducted | May 2026 | - | Pending | Karapitiya Teaching Hospital
16 | Final report submitted | May 2026 | - | Pending | Academic deadline

## Meeting Log
AAC System - Meeting and Review Log
# | Date | Type | Attendees | Key Discussion Points | Actions/Outcomes
1 | Nov 12, 2025 | Supervisor Meeting | Supervisor, Developer | Project scope, AAC gap in Sri Lanka, initial literature direction | Confirmed trilingual scope, agreed on Flutter + TensorFlow stack
2 | Dec 3, 2025 | Sprint 1 Review | Supervisor, Developer | Architecture review, ER diagram feedback, requirements completeness | Minor revisions to ER diagram, approved system architecture
3 | Dec 17, 2025 | Supervisor Meeting | Supervisor, Developer | Literature review findings, FER model options, dataset availability | Agreed on EfficientNetB0 as primary model after MobileNetV2 baseline
4 | Jan 7, 2026 | Sprint 2 Planning | Supervisor, Developer | Sprint 2 backlog priorities, symbol grid design, TTS evaluation | Prioritised core AAC flow, TTS quality flagged as risk
5 | Jan 21, 2026 | Supervisor Meeting | Supervisor, Developer | UI design review, colour palette for ASD suitability, symbol sourcing | Approved soft colour palette, noted Western symbol bias issue
6 | Feb 4, 2026 | Hospital Visit | Clinical staff, Developer | Karapitiya field exposure, communication challenges observed, caregiver feedback | Confirmed offline-first need, simpler grid layout, Sinhala AAC gap validated
7 | Feb 12, 2026 | Sprint 2 Review | Supervisor, Developer | Demo of AAC app, Play Console upload, AI pipeline progress, TTS issues | Approved interim progress, noted Sinhala TTS quality issue for Sprint 3
8 | Feb 20, 2026 | Supervisor Meeting | Supervisor, Developer | Interim report structure, ethics application preparation, methodology discussion | Agreed on Agile Scrum methodology, report structure finalised
9 | Feb 27, 2026 | Informal Discussion | IdeaHub staff, Developer | Potential iOS release via IdeaHub as charitable initiative | Exploratory only, no formal agreement
10 | Mar 5, 2026 | Sprint 3 Planning | Supervisor, Developer | Sprint 3 backlog priorities, symbol licensing strategy, ethics timeline | Prioritised symbol set and ethics submission, model training plan confirmed
11 | Mar 18, 2026 | Supervisor Meeting | Supervisor, Developer | Progress update, interim report feedback, Sprint 3 status check | Report revisions noted, methodology updated to Agile Scrum

## Issue Tracker
AAC System - Issue and Bug Tracker
ID | Sprint | Issue Description | Severity | Status | Resolution | Date Resolved
ISS-001 | Sprint 1 | Flutter iOS build target requires macOS for testing | Medium | Open | Deferred to later sprint, Android-only testing for now | -
ISS-002 | Sprint 2 | Sinhala TTS output quality poor with default Flutter TTS engine | High | Open | Alternative engines under evaluation for Sprint 3 | -
ISS-003 | Sprint 2 | Tamil TTS not functional on all Android devices | High | Open | Device-specific issue, testing on multiple devices planned | -
ISS-004 | Sprint 2 | Google Colab free tier session timeout during training | Medium | Resolved | Aggressive checkpoint saving implemented | Jan 2026
ISS-005 | Sprint 2 | Colab session lost unsaved training progress | High | Resolved | Checkpoint frequency increased to every 5 epochs | Jan 2026
ISS-006 | Sprint 2 | Western-centric AAC symbol sets not suitable for Sri Lankan context | High | In Progress | Manual sourcing and adaptation of culturally appropriate symbols | -
ISS-007 | Sprint 2 | Symbol set licensing terms unclear for open-source redistribution | Medium | In Progress | Legal review ongoing, alternative open sets being explored | -
ISS-008 | Sprint 2 | Test accuracy (66%) significantly lower than validation accuracy (82-84%) | High | Open | Generalisation gap to be addressed in Sprint 3 with more data | -
ISS-009 | Sprint 2 | Default widget_test.dart fails due to MyApp constructor mismatch | Low | Resolved | Test updated to target EmojiText widget directly | Feb 2026
ISS-010 | Sprint 2 | Apple Developer account not available for iOS deployment | Medium | Open | Discussions with IdeaHub (Pvt) Ltd for charitable release | -

## Decision Log
AAC System - Key Decision Log
# | Sprint | Decision | Rationale | Impact
1 | Sprint 1 | Adopted Flutter for cross-platform development | Single codebase for Android and iOS, strong TFLite support, Dart performance | Reduced development effort, enabled dual-platform architecture
2 | Sprint 1 | Selected offline-first architecture with SQLite and JSON | Many target users in rural Sri Lanka lack reliable internet | Core AAC features work without connectivity
3 | Sprint 1 | Chose TensorFlow/Keras for FER model training | Mature ecosystem, extensive documentation, direct TFLite conversion path | Streamlined model development and mobile deployment
4 | Sprint 1 | Designed dual-platform system (Platform A + Platform B) | Platform A for core AAC, Platform B adds FER, allows phased delivery | Reduced complexity per sprint, clear separation of concerns
5 | Sprint 2 | Switched primary model from MobileNetV2 to EfficientNetB0 + CBAM | MobileNetV2 validation accuracy insufficient, EfficientNetB0 showed better feature extraction | Improved validation accuracy from ~75% to 82-84%
6 | Sprint 2 | Used Google Colab for model training instead of local GPU | No local GPU available, Colab provides free T4 GPU access | Enabled deep learning training, but introduced session timeout risk
7 | Sprint 2 | Adopted Agile Scrum (adapted for single developer) | Project is exploratory, requirements evolve, AI training is iterative | Flexible sprint structure, backlog reprioritisation between sprints
8 | Sprint 2 | Used Google Sheets instead of Trello/Jira for tracking | Single developer, mobile accessibility for hospital visits, simpler overhead | Lightweight tracking, accessible on phone during stakeholder meetings
9 | Sprint 2 | Prioritised Android-only testing at interim stage | Apple Developer account not available, Android covers majority of target users | Faster iteration, iOS testing deferred to later sprint
10 | Sprint 2 | Began AI pipeline work ahead of Sprint 3 schedule | Sprint 2 core tasks completed earlier than expected | Head start on model experimentation, identified MobileNetV2 limitations early

## Retrospectives
AAC System - Sprint Retrospective Notes
Sprint | What Went Well | What Could Be Improved | Actions for Next Sprint
Sprint 1 (Nov-Dec 2025) | All planned tasks completed on time Architecture design was thorough Flutter setup smooth for Android Literature review comprehensive | iOS build not testable without macOS Could have started requirements gathering with hospital staff earlier Underestimated symbol sourcing complexity | Begin symbol sourcing early in Sprint 2 Explore hospital visit for field exposure Start AI pipeline setup if time permits
Sprint 2 (Jan-Feb 2026) | Core AAC interface functional and tested AI pipeline work started ahead of schedule Karapitiya visit provided valuable real-world insights Play Console upload successful Checkpoint saving issue resolved quickly | Sinhala/Tamil TTS quality below expectations Symbol licensing more complex than anticipated Colab session timeouts caused lost progress early on Test coverage is minimal | Evaluate alternative TTS engines Resolve symbol licensing before Sprint 3 Increase checkpoint saving frequency Plan broader test coverage for Sprint 3
Sprint 3 (Mar 2026) Current | (In progress - to be completed after Sprint 3 ends) | (In progress - to be completed after Sprint 3 ends) | (In progress - to be completed after Sprint 3 ends)

## Time Log
AAC System - Estimated Time Allocation
Sprint | Activity Category | Estimated Hours | % of Sprint | Notes
Sprint 1 | Literature Review | 40 | 25% | ASD, AAC, FER, Sri Lankan context
Sprint 1 | Requirements Analysis | 24 | 15% | Stakeholder discussions, documentation
Sprint 1 | System Design | 32 | 20% | Architecture, ER, use case, class diagrams
Sprint 1 | Development Setup | 24 | 15% | Flutter, Firebase, project structure
Sprint 1 | Report Writing | 20 | 12% | Project proposal, documentation
Sprint 1 | Supervisor Meetings | 8 | 5% | Reviews and feedback
Sprint 1 | Self-Study | 12 | 8% | Flutter, TensorFlow, Dart tutorials
Sprint 2 | UI Development | 48 | 30% | Symbol grid, navigation, screens
Sprint 2 | AI Model Work | 32 | 20% | Pipeline setup, MobileNetV2, EfficientNetB0
Sprint 2 | Integration | 16 | 10% | TTS, local storage, data layer
Sprint 2 | Testing | 12 | 7% | Unit tests, Play Console, device testing
Sprint 2 | Field Exposure | 8 | 5% | Karapitiya visit and observations
Sprint 2 | Report Writing | 24 | 15% | Interim report preparation
Sprint 2 | Supervisor Meetings | 10 | 6% | Sprint reviews, demo sessions
Sprint 2 | Debugging/Fixes | 10 | 7% | Colab issues, test fixes, TTS evaluation